## Process Map
Team 1 Project Title Reduce lead time of new customer launching Scope Part 1: VTG-CSP receive information from SMM Part 2: Making sample and get customer approval Part 3: MTM2.0 system set up Part 4: System validation and finish pilot run

## FMEA Analysis
Home |  | Potential Failure Mode and Effective Analysis (Process FMEA)
Part Name |  | : |  |  |  | Prepared By : | [5 empty] | Approved By :
Customer Part No. Rev Level. / XYZ Part No. |  | : |  | 9 (cancel business) 6 (customer warning) 3 (minor delay order) 1 (no impact) |  | FMEA Date(orig) : | [5 empty] | Rev Date :
PFMEA No | [5 empty] | Issue Level :
Process Step / Function | Output Requirement | Potential Failure Mode | Potential Effect(s) of Failure | S E V | CLASS | Potential Cause / Mechanism(s) of Failure | Current Process Controls (Prevention) | OCCUR | Current Process Controls (Detection) | D E T | R P N | Recommended Actions | Responsibility | Target Date | Action Results
[15 empty] | Actions Taken | S E V | OCC | D E T | RPN
Part 1: Information transfer between SMM & CSP
1.1 Receive customer information from SMM | 14 items are received from SMM | missing items | postpone the pilot date | 6 | C | do not have standard checklist | no | 6 | When compare with tag list | 6 | 216 | 1. Standardize new program launching checklist 2. Locate in sharepoint (keep update everytime) | Thessa | 2019-04-26
1.1 Receive customer information from SMM | 14 items are received from SMM | not receive information on time | postpone the pilot date | 6 |  | do not have standard checklist | no | 6 | When compare with timeline | 1 | 36
1.2 Review tag list with GT/CMD | Confirm tag list same with sample order file | Tag List not same as order sample file | delay launching date | 6 |  | Tag list and order sample file are not use the latest information | no | 3 | review and feebback issues to SMM team | 1 | 18 | 1. make plan to review, update and communicate with SMM team with data analysis of previous indentification. 2. measure completion % and the aging for corrective action from SMM team. | Queenie | 2019-05-07
1.2 Review tag list with GT/CMD | Confirm tag list same with sample order file | Tag List not same as order sample file | delay launching date | 6 |  | The content in individual sheet is mixxing. | no | 3 | review and feebback issues to SMM team | 1 | 18
1.2 Review tag list with GT/CMD | Confirm tag list same with sample order file | Tag List summary table is different with information inside individual sheet | delay launching date | 6 |  | Tag list and order sample file are not use the latest information | no | 3 | review and feebback issues to SMM team | 1 | 18
1.2 Review tag list with GT/CMD | Confirm tag list same with sample order file | Wrong information appear in each individual sheet not relate to the header | delay launching date | 6 |  | Tag list and order sample file are not use the latest information | no | 3 | review and feebback issues to SMM team | 1 | 18
1.2 Review tag list with GT/CMD | Confirm tag list same with sample order file | Wrong information appear in each individual sheet not relate to the header | delay launching date | 6 |  | wrong typing when key in to order sample. | no | 3 | review and feebback issues to SMM team | 1 | 18
1.2 Review tag list with GT/CMD | Confirm tag list same with sample order file | Error cannot be identified during review session | delay launching date (more impact because detect in later stage) | 9 |  | deviation during review process | no | 3 | detect when receiving testing order in system. | 3 | 81 | 1. data analysis to indentify pattern and root cause. | Linda | 2019-05-07
Part 2: Sample Making Stage
2.1 Sample requirement meeting by CS | GT confirm timeline of prepare fabric, construction method, quality standard, list of machine and folder | Cannot confirm the timeline | Fail OTD | 6 |  | GT is lack of technical knowledge | no | 3 | no | 3 | 54
2.1 Sample requirement meeting by CS | GT confirm timeline of prepare fabric, construction method, quality standard, list of machine and folder | Confirm the date but cannot hit the target delivery date from customer | Fail OTD | 6 |  | Required machine and folder is not ready | no | 3 | when GT check with Mechanic about machine and folder list | 1 | 18
2.1 Sample requirement meeting by CS | CMD confirm timeline of prepare marker, YY and measurement method | Confirm the date but cannot hit the target delivery date from customer | Fail OTD | 6 |  | CMD is lack of manpower | no | 6 | When CMD raise out their timeline to CS and sample room | 1 | 36
2.1 Sample requirement meeting by CS | CMD confirm timeline of prepare marker, YY and measurement method | Confirm the date but cannot hit the target delivery date from customer | Fail OTD | 6 |  | Do not have a standard WBS and timeframe for each step | no | 6 | When CMD raise out their timeline to CS and sample room | 3 | 108 | 1. Alert message pop up when the job is delay/nearly to dealy. Visual management for each job (microsoft project online, sharepoint) 2. Mechanism to estimated time for each work | michael | 2019-05-30
2.1 Sample requirement meeting by CS | CMD confirm timeline of prepare marker, YY and measurement method | Confirm the date but cannot hit the target delivery date from customer | Fail OTD | 6 |  | CMD does not have good prioritze on the job | no | 6 | When CMD raise out their timeline to CS and sample room | 3 | 108 | 1. Process Flow 2. Cycle time 3. Job allocation of each team member | ricky | 2019-05-23
2.1 Sample requirement meeting by CS | Mechanic confirm timeline of prepare machine and folder | Confirm the date but cannot hit the target delivery date from customer | Fail OTD | 6 |  | VTG is lacking machine and folder which need to purchase/make | no | 3 | when GT check with Mechanic about machine and folder list | 1 | 18
2.1 Sample requirement meeting by CS | Sample room confirm timeline of making sample | Confirm the date but cannot hit the target delivery date from customer | Fail OTD | 6 |  | Sample room is lack of manpower | no | 1 | When sample room manager raise out not enough manpower | 1 | 6
2.1 Sample requirement meeting by CS | Sample room confirm timeline of making sample | Confirm the date but cannot hit the target delivery date from customer | Fail OTD | 6 |  | Sample room operator is lack of sewing skill for new construction | no | 3 | When sample room manager raise out not enough manpower | 1 | 18
2.2 Sample Preparation | GT deliver construction method, quality standard, good condition machine and folder to sample room | can not delivery construction method, quality standard, good condition machine and folder to sample room | Fail OTD | 6 |  | GT is lack of technical knowledge | no | 3 | no | 3 | 54
2.2 Sample Preparation | GT deliver construction method, quality standard, good condition machine and folder to sample room | can not delivery construction method, quality standard, good condition machine and folder to sample room |  | 6 |  | Required machine and folder is not ready | no | 3 | when GT check with Mechanic about machine and folder list | 1 | 18
2.2 Sample Preparation | CMD deliver marker to sample room | delivery wrong marker | Fail OTD | 6 |  | CMD staff does not have enough experience | no | 6 | When CMD raise out their timeline to CS and sample room | 3 | 108 | 1. Process Flow 2. Cycle time 3. Job allocation of each team member | ricky | 2019-05-23
2.2 Sample Preparation | CMD deliver marker to sample room | delivery marker later than timeline | Fail OTD | 6 |  | CMD does not have good management job | no | 6 | When CMD raise out their timeline to CS and sample room | 3 | 108 | 1. Process Flow 2. Cycle time 3. Job allocation of each team member | ricky | 2019-05-23
2.2 Sample Preparation | CS deliver sample PS, fabric and trims to sample room | delivery wrong PS information | Fail OTD | 6 |  | human mistake when key in information to PS | no | 1 | when sewing on the line will define wrong information in PS | 3 | 18 | 1. Make the checklist for PS checking 2. Consult GT/SMM/customer for unclear point 3. In pre-development meeting, collect all questions and transfer it into the sample PS 4. in the sample meeting, always ask SR confirmation for the clearance and understanding the PS (Production requirement).
2.2 Sample Preparation | CS deliver sample PS, fabric and trims to sample room | delivery wrong fabric & trim | Fail OTD | 6 |  | CS RO wrong fabric item | no | 3 | end line QC checking to define | 3 | 54
2.2 Sample Preparation | CS deliver sample PS, fabric and trims to sample room | delivery wrong fabric & trim | Fail OTD | 6 |  | correct RO but warehouse delivery wrong fabric | no | 3 | CS checking after receiving from warehouse | 1 | 18
2.2 Sample Preparation | Production and sample room confirm ready to make sample | can not confirm the readiness date to make sample | Fail OTD | 6 |  | have not enough capacity for sample | no | 6 | production manger raise out with sample room | 1 | 36
2.3 Sample Making | Sample is approved by QC and on time | the sample not meet customer workman ship requirement | Fail OTD | 6 |  | the sewing operator skill not meet requirement | no | 6 | Sewing GT define in line | 1 | 36
2.3 Sample Making | Sample is approved by QC and on time | the sample not meet customer workman ship requirement | Fail OTD | 6 |  | machine adjust not proper with garment fabric item | no | 6 | Sewing GT define in line | 1 | 36
2.3 Sample Making | Sample is approved by QC and on time | the sample not meet customer measurement requirement | Fail OTD | 6 |  | CMD provide wrong marker | no | 3 | end line QC inspection | 3 | 54
2.3 Sample Making | Sample is approved by QC and on time | the sample not meet customer measurement requirement | Fail OTD | 6 |  | Cutting panel not eccuracy | no | 3 | Sewing GT define in line | 3 | 54
2.3 Sample Making | Sample is approved by QC and on time | the sample not meet customer measurement requirement | Fail OTD | 6 |  | Sewing allowance incorrection | no | 3 | Sewing GT define in line | 3 | 54
2.4 Send sample to customer | Customer approval on sample | Customer reject | Delay launching date | 6 |  | QC escapse defect | no | 3 | Customer feedback | 3 | 54
3. MTM 2.0 System Set Up
3.1. Order mapping | 1. header is created in MTM2.0 2. Value is set for each header | create wrong header name | can not receive customer order and delay system testing | 6 |  | Customer send wrong order file information | no | 3 | when testing order is fail to receive | 1 | 18
3.1. Order mapping | 1. header is created in MTM2.0 2. Value is set for each header | create wrong header name | can not receive customer order and delay system testing | 6 |  | ISC input wrong value by manually | no | 3 | when testing order is fail to receive | 1 | 18
3.1. Order mapping | 1. header is created in MTM2.0 2. Value is set for each header | set wrong value for header | can not receive customer order and delay system testing | 6 |  | Customer send wrong order file information | no | 3 | when testing order is fail to receive | 1 | 18
3.1. Order mapping | 1. header is created in MTM2.0 2. Value is set for each header | set wrong value for header | can not receive customer order and delay system testing | 6 |  | ISC input wrong value by manually | no | 3 | when testing order is fail to receive | 1 | 18
3.2.Order Filter | All inappropriate option is filtered from MTM2.0 | Missing to filter some options | Receive customer complain due to not able to complete the order | 6 |  | Customer send wrong order file information | no | 3 | when receive customer complain | 9 | 162 | Update in the order mapping, reduce the steps in order filter: - reduce cycle time - reduce risk | Linda | 2019-05-23
3.2.Order Filter | All inappropriate option is filtered from MTM2.0 | Missing to filter some options | Receive customer complain due to not able to complete the order | 6 |  | ISC input wrong value by manually | no | 3 | when receive customer complain | 9 | 162 | Update in the order mapping, reduce the steps in order filter: - reduce cycle time - reduce risk | Linda | 2019-05-23
3.3. Mesurement set up | Measurement chart (including measurement point, tolerance, body measurement) | missing / wrong information | create garment with wrong measurement | 6 |  | human mistake when input wrong/missing information | assign 2nd person to check the measurement information | 1 | immediately find out the mistake by 2nd person | 1 | 6
3.3. Mesurement set up | Measurement chart (including measurement point, tolerance, body measurement) | missing / wrong information | create garment with wrong measurement | 6 |  | human mistake when checking measurement set up information | no | 1 | no | 3 | 18
3.4. Operation Set Up | 1. all style option of each part 2. image of each style option 3. image position in PS | wrong PS | CS need to rework on setting | 3 |  | human mistake when input wrong/missing information | no | 3 | When CS review PS and find out the problem | 3 | 27 | There is a program to check the MTM 2.0 set up
3.4. Operation Set Up | 1. all style option of each part 2. image of each style option 3. image position in PS | wrong PS | CS need to rework on setting | 3 |  | ISC misunderstand internal requirement | no | 3 | internal meeting to align between ISC & T&Q team | 3 | 27
3.4. Operation Set Up | 1. all style option of each part 2. image of each style option 3. image position in PS | unclear image in PS | production complain | 1 |  | no standard for the resolution and size for the image and text | no | 3 | when the PS is received by QC & production | 3 | 9
3.5. Material set up | 1. material code with discription 2. Image 3. Image location in PS 4. Material location in garment 5. Material consumption | Wrong information | create garment with wrong material | 6 |  | human mistake when input wrong/missing information | no | 3 | when the PS is received by QC & production | 3 | 54 | There is a program to check the MTM 2.0 set up
3.5. Material set up | 1. material code with discription 2. Image 3. Image location in PS 4. Material location in garment 5. Material consumption | unclear image in PS | production complain | 1 |  | no standard for the resolution and size for the image and text | no | 3 | when the PS is received by QC & production | 3 | 9
3.6. marker setup | 1. marker 2. Fabric consumption | 1. wrong fabric direction 2. wrong matching rule 3. wrong style option | wrong garment is produced | 3 |  | CMD mistake when input wrong/missing information | no | 3 | Check by cutting | 1 | 9
3.6. marker setup | 1. marker 2. Fabric consumption | 1. wrong fabric direction 2. wrong matching rule 3. wrong style option | wrong garment is produced | 3 |  | GT provide wong information | no | 3 | Check by cutting | 1 | 9
3.7. pick to light | complete material location table (include location code, M3 item code (FW), Material ID) (light on correct material location when scan order) | set up system wrong so light is not turn on in appropriate location | pick wrong item -> rework garment | 3 |  | Set incorrect location and Item code by manual mistake | no | 1 | Check by endline QC | 1 | 3 | there are sofware to check the informaiton between PS and pick to light
3.7. pick to light | complete material location table (include location code, M3 item code (FW), Material ID) (light on correct material location when scan order) | set up system wrong so light is not turn on in appropriate location | pick wrong quantity -> retake material again | 1 |  | Set incorrect quantity by manual mistake | no | 1 | Check by sewing operator | 1 | 1
3.8. date and time | 1. auto-receive-order rule per customer and product 2. shipment schedule rule 3. leadtime 4. capacity | - wrong information input | need to re-set the system by ISC | 1 |  | Set incorrect information by manual mistake | no | 1 | by testing system | 1 | 1
3.9. CO | CO # is matching with schedule # | CO # is not matching with schedule # | cannot complete the FG report | 3 |  | ISC input wrong information by manually | no | 3 | when logistic team can't run invoice | 1 | 9 | There is a program to check create CO in M3 and auto put in MTM2.0
3.10. Other | email configure | Wrong customer email address | customer could not receive report from system | 3 |  | ISC input wrong information by manually | no | 1 | when customer complain due to not receive email from system | 9 | 27
3.11. setup for CCA | Build price per style, fabric and treatment | Incorrect price | higher than normal price -> customer complain | 6 |  | ISC input wrong information by manually | no | 3 | Audit by HK internal audit team | 3 | 54 | There is a program to create SKU maintenain when have ew fabric in CCA with correct price
3.11. setup for CCA | Build price per style, fabric and treatment | Incorrect price | higher than normal price -> customer complain | 6 |  | ISC not follow SOP | no | 3 | Audit by HK internal audit team | 3 | 54
3.11. setup for CCA | Build price per style, fabric and treatment | Incorrect price | lower than normal price -> VTG lost money | 6 |  | ISC input wrong information by manually | no | 3 | Audit by HK internal audit team | 3 | 54
3.11. setup for CCA | Build price per style, fabric and treatment | Incorrect price | lower than normal price -> VTG lost money | 6 |  | ISC not follow SOP | on | 3 | Audit by HK internal audit team | 3 | 54
Part 4. Validate System Set Up
4.1 Create testing order file by ISC manually | Testing order file is created | Create wrong testing file | delay the launching date | 6 |  | ISC does not use the updated tag list | no | 6 | when fail to receive order | 1 | 36 | SMM apply standard template, IT create a program to auto copy information to create test order file |  | there should be standard tag list approved in last year, and the standard list should be put in sharepoint, make sure the information inside are always update
4.1 Create testing order file by ISC manually | Testing order file is created | Create wrong testing file | delay the launching date | 6 |  | don't know how to use xml file | no | 6 | when checking PS | 3 | 108 | auto convert xml to Excel format by using the appplication in Excel 1. Make SOP to guide to convert from XML. file to Excel.file 2. Training SOP for ISC member 3. Validate ISC can convert correctly to Excell. file 4. Moniotor effective of action as reduce wrong cases in creating testing order file step | Cuong | 24.Apr.19
4.2 Copy file to share folder | Share folder includes all required order files for testing | cannot put all required order files in share folder | delay the launching date | 6 |  | network disconnection | no | 3 | when ISC copy the file to share folder | 1 | 18
4.2 Copy file to share folder | Share folder includes all required order files for testing | cannot put all required order files in share folder | delay the launching date | 6 |  | server shut down | no | 3 | when ISC copy the file to share folder | 1 | 18
4.3 Receive testing order file by MTM2.0 | Testing order is recieved | cannot generate PS | delay the launching date | 6 |  | MTM 2.0 error | no | 3 | when ISC try to generate PS | 1 | 18
4.3 Receive testing order file by MTM2.0 | Testing order is recieved | cannot generate PS | delay the launching date | 6 |  | network disconnection | no | 3 | when ISC try to generate PS | 1 | 18
4.3 Receive testing order file by MTM2.0 | Testing order is recieved | cannot generate PS | delay the launching date | 6 |  | server shut down | no | 3 | when ISC try to generate PS | 1 | 18
4.3 Receive testing order file by MTM2.0 | Testing order is recieved | cannot receive testing order | delay the launching date | 6 |  | MTM 2.0 set-up wrong | no | 6 | when testing order is fail to receive | 1 | 36 | There is a program to check the MTM 2.0 set up
4.3 Receive testing order file by MTM2.0 | Testing order is recieved | cannot receive testing order | delay the launching date | 6 |  | test order file wrong | no | 6 | when testing order is fail to receive | 1 | 36
4.4 Check information in PS | All information are correct in PS | Some information are different with tag list and order file | delay the launching date | 6 |  | MTM 2.0 set-up wrong | no | 6 | when PS is print out and check by ISC | 1 | 36 | no need to check PS anymore if MTM 2.0 set up is correct
4.4 Check information in PS | All information are correct in PS | Some information are different with tag list and order file | delay the launching date | 6 |  | test order file wrong | no | 6 | when PS is print out and check by ISC | 1 | 36
4.5 Request HKIT copy UAT to PROD | MTM2.0 is ready in PROD | MTM 2.0 canonot use in PROD | delay the launching date | 6 |  | HKIT miss some parts in UAT | no | 3 | HKIT will inform by email | 1 | 18 | copy automatically
4.5 Request HKIT copy UAT to PROD | MTM2.0 is ready in PROD | MTM 2.0 canonot use in PROD | delay the launching date | 6 |  | ISC miss some parts in UAT | no | 3 | when print PS for all pilot orders | 1 | 18 | copy automatically
Customer Identified Special Characteristics

## Part 1 - Kaizen 1
Kaizen / Poka Yoke
Theme | Standard request list between SMM and CSP |  |  |  |  | Lesson Number
Classification | Basic knowledge | Improvement cases | Trouble cases
Before |  |  |  |  | After
https://talapparel-my.sharepoint.com/:x:/r/personal/kalokwong_talapparel_com/_layouts/15/Doc.aspx?sourcedoc=%7Bb8c5251f-34b1-4f6d-ab4e-a58699cfd59c%7D&action=default&uid=%7BB8C5251F-34B1-4F6D-AB4E-A58699CFD59C%7D&ListItemId=81&ListId=%7B61B783AB-C58A-47B6-8D57-7DF45E2BFEF2%7D&odsp=1&env=prod
REMARKS:. Make the check list to reduce back & force email and save the time to check with SMM team (The detail as above)
Prepared By : Thessa |  |  |  | Approved By :
Date : 25.04.19

## Part 2 - Kaizen 1
ONE POINT LESSON
Theme | Clear workflow, cycle time and job allocation for CMD team |  |  |  |  | Lesson Number
Classification | Basic knowledge | Improvement cases | Trouble cases
Not Good |  |  |  |  | Good
REMARKS: Create standard work flow, cycle time and visual job allocation to CMD team.
Prepared By : Ricky |  |  |  | Approved By : |  |  | Approved By :
Date : 25.04.2019 | [6 empty] | Date :
Not visualized work flow, cycle time and job allocation in CMD team

## Part 3- Kaizen 1
Kaizen / Poka Yoke
Theme | Group in order mapping to reduce lead time and risk in order filer |  |  |  |  | Lesson Number
Classification | Basic knowledge | Improvement cases | Trouble cases
Before |  |  |  |  | After
REMARKS: Set up 1 big group in order mapping for due the time set up in order filter and more exactly.
Prepared By : Linda |  |  |  | Approved By :
Date : 25.04.19

## Part 4 - Kaizen 1
Kaizen / Poka Yoke
Theme | Convert from XML.file to Excell.file |  |  |  |  | Lesson Number
Classification | Basic knowledge | Improvement cases | Trouble cases
Before |  |  |  |  | After
REMARKS:. with convert to Excell file the ISC is easy & familar to use. So, it make reduction human mistake when coppy content during creating testing order file
Prepared By : Cuong |  |  |  | Approved By :
Date : 24.04.19